## Project Tasks and Milestones
Tasks | Start Date | End date | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
1. Planning | 2021-11-01 | 2021-11-05 | 4hr | 8hr
1.1 Look through the Assessment |  |  |  |  | 8hr | 4hr
1.2 Research about topic | [7 empty] | 4hr
1.3 Decide Topic | [8 empty] | 4hr
First Week (Total hours)32
2. Start Making Project | 2021-11-05 | 2021-11-12
2.1 Project proposal |  |  | 4hr | 8hr |  |  |  |  | 2hr
2.2 Working on Modals |  |  |  |  | 8hr
2.3 Create Database | [5 empty] | 4hr |  | 6hr
2.4 Designing Project | [8 empty] | 4hr
Second Week(Total hours)34
3. Documentation | 2021-11-13 | 2021-11-17
3.1 Application Testing |  |  | 4hr | 8hr | 8hr
3.2 Responsiveness | [5 empty] | 4hr |  | 4hr | 4hr
3.3 Usability Testing |  |  | 4hr | 8hr | 8hr
Third Week(Total hours)52
Total hours on Project(118)

## Application Testing
Application Testing
Steps | Details | Expected Result | Actual Result | Pass/Fail/Error
1 | Register page | Register page should open | Register page display | Pass
2 | Login Page | Login page should open | Login page display | Pass
3 | Home Page | Home page should open | Home page display | Pass
4 | Staff Page | Staff page should open | Staff page display | Pass
5 | Reasons Page | Reasons page should open | Reasons page display | Pass
6 | Annual Leave Page | Annual Leave page should open | Annual page display | Pass
7 | Buttons | All buttons should working correctly | All buttons work correctly | Error
8 | Color Schema | White | Displayed | Pass

## Responsiveness
Responsiveness
Home page
Staff Page
Reasons Page
Annual Leave Page
Login Page
Register Page

## Usability Testing
Usability And Acessability | Agree | Disagree | Comments
The application is loaded
The page is self explanatory and i know how to use it
Functionality
All buttons works correctly
Crud operation
Can, edit, delete and view details |  |  | There is one error in delete staff entry which is coming from database
Readibility
The font is easy to read
The Size and style of the font is easy to read |  |  |  | s
The combination between text color and background looks easy to read
Sufficient spacing
Purpose
The application is fulfill its purpose
The application is suitable for the target audience